## Slide 1: RADA’s management of the rehabilitation of farm roads
PERFORMANCE AUDIT REPORT

## Slide 2: Key Data
RADA is responsible for maintaining farm roads island wide
RADA is the implementing agency for the Farm Road Rehabilitation Programme (FRRP), since October 2015
Jamaica’s farm road network is estimated at 1,500 km.

## Slide 3
Purpose of the Audit
To assess the effectiveness of the quality management of farm roads
To assess whether the GOJ, through RADA, had in place an effective management system for the rehabilitation of Jamaica’s farm roads

## Slide 4: GOJ’s Vision for Jamaica’s Farm Roads
Vision 2030 National Development Plan (NDP)
To improve and rationalize the road network including farm road network by improving agriculture feeder road.
The National Transport Policy (2007)
Transport vital for human development, in terms of access to markets and basic services.
Agriculture’s Contribution to Jamaica’s Sustainable Development
(2010)
Investment in agricultural research and rural roads typically produces returns that are two to six times greater than those produced by providing input subsidies.
UN Sustainable Development Goal
# 9
Investment in infrastructure and innovation are crucial drivers of economic growth and development.

## Slide 5: Trend Analysis of RADA’s Farm Roads Rehabilitation Programme
Chart: 
| 2015-2016 | 2016-2017 | 2017-2018 | 2018-2019
Budget Request $ ('000) | 500000 | 300000 | 1500000 | 834720
Budget Allocation $ ('000) | 459747 | 250000 | 470000 | 800000
Amount Received $ ('000) | 452747 | 257684 | 370367 | 759417
Amt. received as % of requested | 0.90549 | 0.85895 | 0.24691 | 0.90979
Amt. received as % of Allocation | 0.98477 | 1.0307 | 0.78801 | 0.94927

## Slide 6: KEY FINDING: RADA’s budget request for the management of farm roads was limited to the Farm Road Rehabilitation Programme (FRRP)
Annual Budget Requests
RADA’s annual funding requests were limited to the rehabilitation of 50 km of priority roads under the FRRP.
RADA’s Strategic Business Plan (SBP)
There was no consistent relationship (alignment) between RADA’s budget outlined in the SBP and that requested from MICAF
Diversion of Funds
RADA failed to provide evidence that MICAF approved the diversion of funds allocated for farm roads, towards the repair of non-farm roads.
Budget submissions and plans did not include funding for routine, preventative & emergency repairs.
No reasons provided for the difference, which limited transparency of the budget process and accountability.

## Slide 7: KEY FINDING: RADA could not readily distinguish between farm roads and the parochial roads managed by municipal corporations.
RADA established annual priority lists for the selection of farm roads to be rehabilitated but could not explain the basis for the selection of some farm roads
This raised doubts regarding the transparency of the selection process.
RADA admitted that its definition of farm roads was inadequate and outdated.

## Slide 8: Key Finding: RADA could not identify which of the following criteria the roads on its priority list satisfied.
RADA advised that the lack of financial and human resources hampered their ability to measure the economic impact of the farm road rehabilitation. In the interim, sensitization sessions were initiated during its quarterly performance review meetings, in order to give senior management an appreciation of the importance of impact evaluation.

## Slide 9: Key Finding: RADA lacked a proper roads management system to support its road rehabilitation programme.
A robust road inventory management system would provide information necessary for the proper determination and prioritization of resources including the current status of farm roads, to guide the rehabilitation activities.
RADA intends to develop a system that would identify roads by (GPS), distance, condition of surface, drainage, estimate of works to be done, number of farmers served, agricultural production in the area (type of enterprise, hectarage in use and output) and expected impact of the rehabilitation investment among other demographics.

## Slide 10: Key Finding: RADA’s process of selecting contractors was not always transparent or competitive. RADA was unable to indicate the basis on which the contractors engaged by LT methodology were pre-selected for invitation to bid on road rehabilitation contracts.
$1b
75 contracts awarded by inviting pre-selected contractors
$521m
33 contracts awarded directly or for emergency
$91m
4 contracts awarded on competitive basis

## Slide 11: Key Finding: RADA’s process of selecting contractors was not always transparent or competitive. RADA’s justification for the use of the direct and emergency procurement methodologies did not conform with GOJ guidelines. The reasons cited by RADA were:
The need to expend the budgetary allocation for the farm road rehabilitation programme before the end of the financial year
The impact of land slippage and deterioration of the road surface due to continuous rainfall over the past 4 to 6 months
The selected contractor was already mobilised and engaged on similar projects in the parish or neighbouring parishes
The contractors possessed the necessary expertise and capability to perform the works satisfactorily and within budget

## Slide 12: Key Finding: RADA’s omission of critical specifications from road rehabilitation contracts, coupled with the absence of routine and regular maintenance, heightened the risk of sub-standard works.
RADA frequently re-scoped road works by excluding elements such as drains and culverts, deemed key components of road infrastructure that could ensure its longevity. RADA also changed the location of contracted works without any evidence of re-measurements.
Survey of farmers revealed that while some acknowledged that repaired roads made it easier to get to and from their farms and reduced wear and tear on their motor vehicles, many complained of poor drainage on some newly rehabilitated roads.

## Slide 13: Key Finding: RADA’s inspection and monitoring activities were inconsistent with its quality assurance framework.
RADA developed guidelines related to key quality requirements for general work activities along with an inspection checklist.
Works engineers made no notations on inspection checklists regarding the nature, frequency of testing and physical conditions of the roads during monitoring and inspection.
RADA’s Internal Audit Reports highlighted issues that supported AuGD’s concern that RADA did not take steps to assure itself that roads were rehabilitated to quality standards.

## Slide 14
GOING FORWARD
RADA should review its current systems to ensure adherence to quality standards and guidelines, related to its road works.
RADA should consider coordination with PIOJ and STATIN to enable the measurement of the economic impact of road rehabilitation.
RADA needs to align its strategic plan to embrace routine, preventative and emergency repairs.
RADA should consider implementing a road inventory management system for roads under its purview.
Recommendations