## Slide 1: Performance Audit Report Management System For The Maintenance Of Parochial Roads
Kingston and Saint Andrew Municipal Corporation (KSAMC)
December 2020

## Slide 2: Audit Objectives
To determine whether KSAMC had in place an effective and efficient management system for maintenance of parochial roads.
Assess whether value for money was achieved for funds spent on the rehabilitation and maintenance of parochial roads.

## Slide 3: Key Data
KSAMC master list of 1,793 parochial roads (606 km), was last updated in 1992.
$3.3 billion spent from the Parochial Revenue Fund for road maintenance, over the period 2014-2015 to 2019-2020.

## Slide 4: Management Team & Staff
KSAMC has qualified management team and trained staff; nonetheless the Corporation’s effectiveness was weakened by a lack of planning documents to promote greater accountability and mitigate costly errors.
The Direct responsibility for the management of parochial roads resided with the City Engineering Department; however the department was short of 4 critical staff (1 deputy superintendent and 3 field officers)
Notwithstanding, the City Engineering staff possessed the requisite skillsets and expertise to effectively carry out their duties.

## Slide 5: Governance and Oversight
Absence of effective systems to manage road works, combined with deficiencies in the Council’s oversight framework, would have hindered KSAMC from achieving full value from money spent on road maintenance and rehabilitation works.
Deficiencies in Monitoring & oversight
Parochial road network vulnerable to risk of deterioration
No strategic plan & risk Assessment

## Slide 6: Financial Management
Budgets not aligned to annual road maintenance plans for parochial roads.
Budgets mainly based on trends in allocations of previous years and not on identified needs.
Some accounting records could not be reconciled.
KSAMC’s Budgetary Process

## Slide 7: Financial Management
Owing to an absence of updated parochial road inventory, the AuGD could not be assured that:
  The amounts of $3.7 billion, allocated by MLGRD between 2014-2015 and 2019-2020, represented an accurate calculation of amounts due.

## Slide 8: Financial Management
Categories of PRF expenditure and percentage of total PRF spent for road works during the period 2014-2020. Activities consisted of:
  Road repairs
  Patching
  Drainage
  Bushing
Chart: 
| KSAMC & PRF Programmes | Special Grant for Repairs | Divisional Allocation Fund | Administration Cost
 | 1859033760 | 234973480.0714 | 1159912138 | 39086729

## Slide 9: Strategic Management and Oversight
KSAMC’s Council failed to consistently develop strategic plans or performance targets for the delivery of cost-effective quality road works.
No strategic approach to the allocation of scarce resources for the maintenance parochial road network.
The requisite Audit Committee to facilitate adequate oversight of the Corporation’s operations was not established.
KSAMC was limited in its ability to hold staff of the City Engineering Department to account in their service delivery.

## Slide 10: Strategic Management
The Absence of a consistent strategic approach to road maintenance heightened the risk of critical scarce resources being diverted from road projects that:
(a) have greater impact on public safety, (b) facilitate greater economic and social benefits for communities and stakeholders.

## Slide 11: Roads Management
KSAMC did not maintain critical information about the condition of parochial roads to guide maintenance activities.
KSAMC inspection activities did not provide assurance that road maintenance work undertaken, always complied with quality standards.
KSAMC monthly work programmes were not always reflective of planned road works.

## Slide 12: Roads Management
A reduction in preventative and routine road maintenance between 2014-2015 to 2016-2017 undermined the preservation of adequate road conditions for the public.
Financial Year | Road Repairs | Patching | Drainage | Bushing
 | km | m2 | km | km
2016-2017 | 5.1 | 14,710 | 14.129 | 42.1
2015-2016 | 5.54 | 20,060 | 14.679 | 121.77
2014-2015 | 30.12 | 18,600 | 102 | 90
Total | 40.76 | 53,370 | 130.808 | 253.87

## Slide 13: Procurement and Contracts Management
KSAMC’s contracts management system did not capture all critical records to facilitate efficiency and transparency.
We could not confirm that KSAMC adhered to all requisite procurement guidelines

## Slide 14: What should be done - MLGRD
Fast-track the approval of a comprehensive long-term plan with priority activities and targets for road maintenance, to achieve and deliver a quality road network.
Enforce KSAMC’s submission of strategic plans for approval, as required by the Local Government (Financing and Financial Management) Act, 2016

## Slide 15: What should be done - KSAMC
Maintain an up -to- date contracts management system that integrates manual and electronic systems to facilitate retrieval, tracking and monitoring of contract data.
Develop workplans and targets to inform coordination of activities identified in annual operational plans and provide a basis for assessing staff performance.

## Slide 16: ‘A better Country through effective audit scrutiny’