## Slide 1: Managing The Main Road Network
Auditor General’s Department, Jamaica
Performance Audit Report
2023 June 06

## Slide 2: GOJ’s vision for Jamaica’s Road Network
SDG #9: Industry, Innovation and Infrastructure
Vision 2030 National Development Plan (NDP)
The National Transport Policy (2007)
Transport vital for human development, in terms of access to markets and basic services.
Build strong economic infrastructure by the expansion and rationalisation of land transport and infrastructure services.
Target 9.1 - Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation.

## Slide 3: GOJ’s INVESTMENT IN THE MAIN Road Network
The Government invested $27.41 billion for road maintenance works between 2016-17 and 2021-22 and through the NWA engaged the services of contractors and consultants to carry out these and capital road projects.

## Slide 4: Audit Objective
  To assess whether the National Works Agency’s (NWA) management of Jamaica’s main roads was cost-effective and agile. The audit focused on:
  The National Works Agency’s management of major road projects namely, the MIDP, the Junction Main Road rehabilitation and a preliminary review of the SCHIP.

## Slide 5: KEY FINDINGS
Geotechnical, hydrological, and geological issues, among other factors, led to additional costs totaling $882.13M for the Junction Main Road rehabilitation works.
Five of the six road projects experienced additional time and costs, due to project rescoping, implementation delays and price variations.
NWA fully implemented 5 of 6 six recommendations from our 2011 special audit report on the Jamaica Development Infrastructure Programme (JDIP).

## Slide 6: Major Infrastructure Development Programme
The Mandela Highway, Constant Spring Road, Hagley Park Road, and Ferris Cross to Mackfield all experienced significant rescoping during the construction and rehabilitation phases of works.
Hence, additional costs for 4 of the road works projects totaled US$16.54M, while NWA saved US$351,860 (1.7%) on the Marcus Garvey Drive Improvement Project.
GOJ’s decision to replace water and sewerage pipelines after the commencement of works on4 MIDP contributed to additional project cost of US$46.9 million.
NWA incurred higher than anticipated costs of US$3.9 million for boundary and ancillary works for Constant Spring and Hagley Park Road Projects

## Slide 7: Junction Main Road rehabilitation works
In August 2016, Cabinet approved the award of the contract (Package 1) for $597.77 million to upgrade the Junction Road Corridor. However, the project experienced increased cost totalling $882.13 million due mainly to:
Delay in land acquisition to enable construction works and unforeseen geotechnical and geological issues which resulted in delays (prolongation cost) costing $70.05 million.
As a consequence of the delays, price increases in labour and materials costs totalling $203.15 million due to extension of time up to July 2019.
Design Changes resulting in the construction of new retaining walls for slope protection and improved /additional drainage structures to remedy unfavourable soil conditions, geological and hydrological conditions during the construction phase totalling $246.79 million.

## Slide 8: Southern Coastal Highway improvement programme (SCHIP)– IMPACT ON PROGRESS
i. Land Acquisition
Outstanding relocation of utility poles contributed to delays across the sub-contracts; exacerbated by delays by the electricity utility provider in the sourcing of the requisite materials to relocate their assets along the project corridor.
iii. Upgrading of NWC’s water and sewerage pipelines
Cabinet approved the extension of project timeline to permit the upgrading of NWC’s water and sewerage pipelines that ran along the project corridors and instructed that the related works be carried out in tandem with the road works.
ii. Relocation of Utility poles
Up to the date of our assessment (April 2023) NWA did not hand over 108 (19.5%) of 553 parcels to the Main Contractor

## Slide 9: Conclusion
Project plans and budgets were often revised, resulting in significant delays and additional costs.

## Slide 10: OPPORTUNITIES TO IMPROVE
Better coordination and resource planning using a Whole-of-Government Approach (WGA)
MEGJC and NWA should adopt a whole of Government approach for the implementation of major road infrastructure projects.

## Slide 11
OPPORTUNITIES TO IMPROVE
Steps should be taken at the pre-contract stages of project implementation to ensure that designs consider all pre-requisites, infrastructure needs and terrain to minimize modification during the implementation stage. This could better inform budgetary requirements.

## Slide 12: ‘A better Country through effective audit scrutiny’